## Traceability
Review Master - User Story Traceability Matrix
Each story mapped to backend module, architecture section, API endpoints, tables, agents/skills, delivery phase and test approach. All references were checked against openapi.yaml, DATA_MODEL.md, SKILLS.md and AGENTS.md at build time.
Version | Story ID | Title | Role | Priority | Status | Phase | Sprints | Backend module(s) | Architecture reference | API endpoints | Key tables | Agents / skills | Flow | Test approach | Notes / gaps
V1 | US-002 | Resolve canonical product and variant | Consumer | Must Have | Draft | Phase 1 | S2-S4 | catalog | Architecture §3.4; ADR-0006 | POST /api/v1/products/identify | product_families, listings, product_mappings, match_candidates, variants | match_product, resolve_variant, Identity Matching Assistant | SEQUENCE §1 | Unit tests of matching order; labeled-set accuracy method (TEST_STRATEGY §4)
V1 | US-003 | Correct product identification | Consumer | Must Have | Draft | Phase 1 | S2-S4 | catalog + admin | Architecture §3.4 | POST /api/v1/products/corrections | product_corrections, audit_log | - | SEQUENCE §1 | Integration: a user correction never changes the global mapping; audit row exists
V1 | US-004 | View normalized specifications | Consumer | Must Have | Draft | Phase 1 | S2-S4 | normalization | Architecture §3.5 | GET /api/v1/variants/{variant_id} GET /api/v1/products/{product_id} | categories, variants | normalize_specs, convert_units | - | Unit + property tests (units, missing is null, conflicting sources shown)
V1 | US-005 | Search products on the website | Consumer | Must Have | Draft | Phase 1 | S2-S4 | catalog | DATA_MODEL §4 (pg_trgm search) | GET /api/v1/products | products | - | - | Integration: search ranking, empty and misspelled queries
V1 | US-033 | Manage users, roles, and permissions | Admin | Must Have | Draft | Phase 1 | S2-S4 | auth + admin | Architecture §3.16; SECURITY §2 | GET /api/v1/users/me GET /api/v1/admin/users PUT /api/v1/admin/users/{user_id}/roles | users, memberships, audit_log | check_permission, log_trace | SEQUENCE §5 | Escalation tests; role change audited; MFA for admin/expert | Admin user/role endpoints added to the API skeleton
V1 | US-034 | Manage categories and versioned evaluation models | Admin | Must Have | Clarification Required | Phase 1 | S2-S4 | evaluation + admin | EVALUATION_MODEL_SPECS; ADR-0004 | GET /api/v1/admin/evaluation-models GET /api/v1/admin/evaluation-models/{model_id} POST /api/v1/admin/evaluation-models/{model_id}/versions POST /api/v1/admin/evaluation-model-versions/{version_id}/publish | evaluation_models, evaluation_model_versions, audit_log | log_trace | - | Publish rejected if any weight/threshold is null or weights do not sum to 1.0; published version immutable | Domain experts must supply weights and thresholds
V1 | US-035 | Manage product mappings and ambiguous matches | Admin | Must Have | Draft | Phase 1 | S2-S4 | admin + catalog | Architecture §3.4 | GET /api/v1/admin/mappings/queue POST /api/v1/admin/mappings/{item_id}/resolve | product_mappings, match_candidates, audit_log | log_trace | - | Versioned mapping change; split reassigns evaluations correctly
V1 | US-036 | Protect and manage evidence | Admin | Must Have | Draft | Phase 1 | S2-S4 | evidence + admin | Architecture §3.6 | POST /api/v1/evidence POST /api/v1/evidence/{evidence_id}/versions | evidence, evidence_versions, evidence_documents | check_upload_safety, attach_trust_tier | SEQUENCE §2 | Disguised executable rejected; replacing evidence keeps the old version
V1 | US-037 | Audit log of material changes | Admin | Must Have | Draft | Phase 1 | S2-S4 | admin | Architecture §3.17; DATA_MODEL §3 | GET /api/v1/admin/audit-log | audit_log, ai_runs | log_trace | - | App role has INSERT only; failed actions also recorded
V1 | US-006 | View product page with separated trust outputs | Consumer | Must Have | Draft | Phase 2 | S4-S7 | evaluation + community + expert (read) | Architecture §3.1, §3.7; AGENTS §10 | GET /api/v1/variants/{variant_id} | evaluations, feedback, expert_assessments, offers | Response Assembler | SEQUENCE §1 | Contract test: three outputs separate; no blended score field exists
V1 | US-008 | Deterministic category-based evaluation | Consumer | Must Have | Clarification Required | Phase 2 | S4-S7 | evaluation | Architecture §3.7; ADR-0003, ADR-0004; EVALUATION_MODEL_SPECS | GET /api/v1/variants/{variant_id}/evaluation | evaluation_model_versions, evaluations, parameter_results | score_parameter, resolve_evidence_conflict, renormalize_weights, compute_confidence, aggregate_evaluation | SEQUENCE §2 | Golden determinism gate in CI; same score across extension/web/API | Needs decision on `value` (ADR-0005) and approved models
V1 | US-009 | View Review Master score and parameter scores | Consumer | Must Have | Draft | Phase 2 | S4-S7 | evaluation | Architecture §3.7, §4 (cache) | GET /api/v1/variants/{variant_id}/evaluation | evaluations, parameter_results | cache_lookup, compute_value_signal | SEQUENCE §1 | Performance test: cached retrieval about <= 2 s (NFR)
V1 | US-010 | View confidence level separate from score | Consumer | Must Have | Clarification Required | Phase 2 | S4-S7 | evaluation | Architecture §3.7 rules 6-10 | GET /api/v1/variants/{variant_id}/evaluation | evaluations | compute_confidence, compute_freshness | SEQUENCE §2 | Golden fixtures: thin evidence, missing critical parameter, coverage floor | Thresholds are heuristics to calibrate
V1 | US-011 | Inspect evidence and its provenance | Consumer | Must Have | Draft | Phase 2 | S4-S7 | evidence | Architecture §3.6 | GET /api/v1/evidence/{evidence_id} GET /api/v1/evidence/{evidence_id}/versions | evidence, evidence_versions, evidence_documents | attach_trust_tier, classify_source_label | SEQUENCE §2 | Unit: a manufacturer source can never get an 'independent test' label; permission test on private evidence
V1 | US-013 | View evaluation history | Consumer | Should Have | Draft | Phase 2 | S4-S7 | evaluation | Architecture §3.7 (versioning); ADR-0004 | GET /api/v1/variants/{variant_id}/evaluation/history | evaluations | - | SEQUENCE §2 | DB test: no UPDATE/DELETE on evaluations for the app role
V1 | US-001 | Detect product on supported marketplace page | Consumer | Must Have | Clarification Required | Phase 3 | S6-S10 | Extension + catalog | CLIENTS_EVENTS_RELIABILITY §1; Architecture §3.1, §3.4 | POST /api/v1/products/identify | listings, proposed_attributes | match_product, Product Extraction Agent | SEQUENCE §1 | Playwright extension suite (supported/unsupported/API down/ambiguous); manifest permission gate in CI | Blocked by decision #1 (V1 marketplace)
V1 | US-018 | Compare products side by side | Consumer | Must Have | Draft | Phase 3 | S6-S10 | comparison | Architecture §3.11 | POST /api/v1/comparisons | comparisons | build_comparison_matrix | - | Cross-category blocked; insufficient-evidence product shown, not ranked as zero
V1 | US-020 | Discover alternatives | Consumer | Must Have | Draft | Phase 3 | S6-S10 | comparison | Architecture §3.11 | GET /api/v1/variants/{variant_id}/alternatives | variants, evaluations | build_comparison_matrix | - | Eligible-only alternatives; low-confidence flagged
V1 | US-021 | Enter requirements in natural language | Consumer | Must Have | Draft | Phase 3 | S6-S10 | recommendation + ai | Architecture §3.10; AGENTS §2 | POST /api/v1/recommendations/requirements | ai_runs | Requirement Extraction Agent, validate_requirements_schema, sanitize_untrusted_text | SEQUENCE §3 | Schema validation, ambiguous budget asks user, injection ignored
V1 | US-022 | Apply hard constraints before ranking | Consumer | Must Have | Draft | Phase 3 | S6-S10 | recommendation | Architecture §3.10 rules 1, 3 | POST /api/v1/recommendations | recommendations | apply_hard_constraints, suggest_constraint_relaxation | SEQUENCE §3 | Over-budget 9.2-scored product is excluded; empty result gives relaxation hint
V1 | US-023 | Personalized recommendations with explanation | Consumer | Must Have | Draft | Phase 3 | S6-S10 | recommendation + ai | Architecture §3.10; AGENTS §8 | POST /api/v1/recommendations | recommendations, ai_runs | rank_candidates, Recommendation Explanation Agent, validate_grounding, emit_event | SEQUENCE §3 | Determinism of ranking; explanation cites only ranking fields | Ranking factors are heuristics
V1 | US-007 | Save products | Consumer | Should Have | Draft | Phase 3 | S6-S10 | user_space | DATA_MODEL §1.8 | GET /api/v1/saved-products POST /api/v1/saved-products DELETE /api/v1/saved-products/{saved_id} | saved_products | emit_event | - | Integration + RLS: user cannot read another user's saved list
V1 | US-012 | AI explanation of an evaluation | Consumer | Should Have | Draft | Phase 3 | S6-S10 | ai | Architecture §3.13; AGENTS §6 | POST /api/v1/evaluations/{evaluation_id}/explanation | ai_runs | Evaluation Explanation Agent, validate_grounding, sanitize_untrusted_text | - | AI contract tests: grounding, injection, empty input, template fallback
V1 | US-019 | AI comparison summary | Consumer | Should Have | Draft | Phase 3 | S6-S10 | ai | AGENTS §7 | POST /api/v1/comparisons | ai_runs | Comparison Summary Agent, validate_grounding | - | AI contract: only comparison payload data; no blended verdict | Summary is the `summary` field of the comparison response
V1 | US-024 | Manage my preferences | Consumer | Should Have | Draft | Phase 3 | S6-S10 | user_space | DATA_MODEL §1.8 | GET /api/v1/preferences PUT /api/v1/preferences | user_preferences | - | - | Validation + privacy (own data only)
V1 | US-014 | Submit structured feedback | Public Reviewer | Must Have | Draft | Phase 4 | S9-S12 | community | Architecture §3.8 | POST /api/v1/variants/{variant_id}/feedback | feedback | rate_limit_check | - | Integration: guest blocked, pending-until-moderated, own-edit only
V1 | US-015 | View community insights | Consumer | Must Have | Draft | Phase 4 | S9-S12 | community + ai | Architecture §3.8; AGENTS §5 | GET /api/v1/variants/{variant_id}/community | review_analysis, feedback | Feedback Intelligence Agent | - | AI contract: every theme cites feedback_ids; community never changes the score
V1 | US-017 | Moderate community feedback | Admin | Must Have | Draft | Phase 4 | S9-S12 | admin + community | Architecture §3.8, §3.17 | GET /api/v1/admin/moderation/queue POST /api/v1/admin/feedback/{feedback_id}/moderate | moderation_actions, audit_log | log_trace, emit_event | - | Role test: non-admin denied; audit row per decision
V1 | US-025 | View current offers | Consumer | Must Have | Clarification Required | Phase 4 | S9-S12 | pricing + adapters | Architecture §3.12 | GET /api/v1/variants/{variant_id}/offers | offers, listings | compute_freshness | SEQUENCE §6 | Stale-offer flag; permitted sources only (adapter fixtures) | Needs decision #1 and data-licensing answer
V1 | US-016 | Review-quality signals | Consumer | Should Have | Draft | Phase 4 | S9-S12 | community | Architecture §3.8 | GET /api/v1/variants/{variant_id}/community | review_quality_signals | detect_near_duplicates, detect_review_bursts, build_review_quality_signals | - | Fixtures: burst of near-identical reviews flags; one harsh review does not; UI never says 'fake'
V1 | US-026 | View price history | Consumer | Should Have | Clarification Required | Phase 4 | S9-S12 | pricing | Architecture §3.12 | GET /api/v1/variants/{variant_id}/price-history | price_records | get_price_context, record_price_observation | SEQUENCE §6 | Coverage reported; no forecast returned | Depends on permitted price data
V1 | US-027 | Create price and target-price alerts | Consumer | Should Have | Draft | Phase 4 | S9-S12 | pricing + notifications | Architecture §3.12, §3.15 | GET /api/v1/price-alerts POST /api/v1/price-alerts DELETE /api/v1/price-alerts/{alert_id} | price_alerts, notifications | evaluate_price_alert, record_price_observation | SEQUENCE §6 | Cooldown and oscillation tests; alert off switch
V1 | US-028 | Control notification types | Consumer | Should Have | Draft | Phase 4 | S9-S12 | user_space + notifications | Architecture §3.15 | GET /api/v1/notification-settings PUT /api/v1/notification-settings | notification_settings, notifications | - | - | Disabled channel sends nothing; throttling/grouping
V1 | US-029 | Create investigation case from potential issue | Admin | Should Have | Clarification Required | Phase 4 | S9-S12 | expert + admin | Architecture §3.9 | POST /api/v1/expert-cases | expert_cases, audit_log | log_trace | SEQUENCE §4 | Workflow tests; duplicate-case warning | Expert workflow V1 vs V2 (decision #3)
V1 | US-030 | Assign expert with conflict-of-interest check | Admin | Should Have | Clarification Required | Phase 4 | S9-S12 | expert + admin | Architecture §3.9 | POST /api/v1/expert-cases/{case_id}/assign | experts, expert_assignments, coi_declarations | check_permission | SEQUENCE §4 | Conflict blocks assignment; decline returns case to pool | Decision #3
V1 | US-031 | Submit expert assessment with proof | Expert Reviewer | Should Have | Clarification Required | Phase 4 | S9-S12 | expert + evidence | Architecture §3.9 | POST /api/v1/expert-cases/{case_id}/assessments | expert_assessments, evidence_documents | check_upload_safety | SEQUENCE §4 | Own-case only; malicious upload rejected; cannot change a published score | Decision #3
V1 | US-032 | Quality review and publish expert assessment | Admin | Should Have | Clarification Required | Phase 4 | S9-S12 | expert + evaluation | Architecture §3.9 | POST /api/v1/expert-assessments/{assessment_id}/review | expert_assessments, evidence_versions, evaluations | attach_trust_tier, aggregate_evaluation, emit_event | SEQUENCE §4 | Author cannot approve; approval creates tier-1 evidence and a new evaluation row | Decision #3
V1 | US-038 | Monitor integrations and system health | Admin | Should Have | Draft | Phase 4 | S9-S12 | admin + catalog (adapters) | ARCHITECTURE_VIEWS §6 | GET /api/v1/admin/integrations | integrations, jobs | emit_event | - | Simulated adapter failure raises integration.error and shows on the dashboard
V1 | US-039 | Keep commercial relationships out of scoring | Admin | Must Have | Draft | Phase 5 | S11-S13 | all (negative requirement) | SECURITY §2-3 (threat 7); ADR-0003 | None (negative requirement) | audit_log | check_permission | - | No endpoint accepts a score; brand/API-key attempts denied; affiliate flag has no effect on output | Enforced by the absence of a write path plus RBAC tests
V1 | US-040 | Access versioned secure APIs | Developer / API Consumer | Must Have | Draft | Phase 5 | S11-S13 | API layer + auth | Architecture §3.2, §3.16 | GET /api/v1/api-keys POST /api/v1/api-keys DELETE /api/v1/api-keys/{key_id} | api_keys, usage_events | generate_api_key, verify_api_key, rate_limit_check, meter_usage | SEQUENCE §5 | 401/403/429 matrix; idempotency-key replay; key scope, expiry, revocation
V1 | US-041 | Receive signed webhooks for events | Developer / API Consumer | Should Have | Clarification Required | Phase 5 | S11-S13 | events | CLIENTS_EVENTS_RELIABILITY §4 | GET /api/v1/webhooks POST /api/v1/webhooks DELETE /api/v1/webhooks/{webhook_id} GET /api/v1/webhooks/{webhook_id}/deliveries POST /api/v1/webhooks/{webhook_id}/deliveries/{delivery_id}/replay | webhooks, webhook_deliveries, event_outbox | emit_event, sign_webhook | SEQUENCE §2 | Signature verification, tamper, retry/backoff, replay | Webhook scope still open
V2 | US-042 | Conversational product Q&A | Consumer | Should Have | Draft | V2 | after pilot | ai (chat) | Architecture §3.13; AGENTS §9 | POST /api/v1/chat/messages | ai_runs | Conversational Q&A Agent, Orchestrator, validate_grounding, check_permission | - | Tool permission, confirmation for write tools, injection, empty tool results
V2 | US-043 | Buy / track / wait guidance | Consumer | Should Have | Draft | V2 | after pilot | pricing | Architecture §3.12 | Planned - not in skeleton | price_records | buy_track_wait_guidance, get_price_context | - | Rule-based cases incl. sparse data | Endpoint to be specified in V2
V2 | US-044 | Add an authorized marketplace adapter | Admin | Should Have | Draft | V2 | after pilot | catalog + admin (adapters) | Architecture §3.4; ARCHITECTURE_VIEWS §5 | Planned - not in skeleton | marketplaces, integrations | - | - | Second adapter leaves canonical evaluation unchanged | Endpoint to be specified in V2
V2 | US-048 | Product-intelligence commercial API | Developer / API Consumer | Should Have | Draft | V2 | after pilot | API layer + auth | Architecture §3.16 | GET /api/v1/api-keys | api_keys, usage_events, organizations | meter_usage, rate_limit_check | SEQUENCE §5 | Tenant isolation, plan limits | Plans/billing endpoints planned (decision #7)
V2 | US-045 | Mobile app: share URL and compare | Consumer | Could Have | Draft | V2 | after pilot | mobile client | CLIENTS_EVENTS_RELIABILITY §3 | Reuses V1 endpoints | - | - | - | Share-URL flow; no private data of other apps | Framework decision at V2 start
V2 | US-046 | Post-purchase feedback with purchase verification | Public Reviewer | Could Have | Draft | V2 | after pilot | community | Architecture §3.12 (click vs purchase) | Planned - not in skeleton | feedback | check_upload_safety | - | Click is not a purchase; receipt privacy | Endpoint to be specified in V2
V2 | US-047 | Brand profile and evidence submission | Brand / Manufacturer | Could Have | Clarification Required | V2 | after pilot | admin + evidence (brand) | Architecture §3.16 | Planned - not in skeleton | evidence | attach_trust_tier | - | Brand cannot edit scores; evidence labelled manufacturer-published | Endpoint to be specified in V2
V2 | US-049 | Retrieve answers from approved documents (RAG) | Consumer | Could Have | Draft | V2 | after pilot | ai (RAG) | Architecture §3.14; ADR-0015 | POST /api/v1/evidence | evidence_documents | semantic_search, apply_trust_weighting, check_upload_safety | - | Only approved documents retrieved; empty result valid; never feeds scoring | Ingestion endpoint to be specified in V2
V3 | US-050 | Context-aware questions via context graph | Consumer | Could Have | Draft | V3 | after V2 | ai (context graph) | Architecture §5 (Neo4j profile) | Planned - not in skeleton | - | graph_lookup | - | User-scoped graph queries | V3
V3 | US-051 | Predictive price and quality-change detection | Consumer | Could Have | Draft | V3 | after V2 | pricing + evaluation | Architecture §3.12 | Planned - not in skeleton | price_records, evaluations | - | - | Estimates labelled; no strong prediction on weak data | V3
V3 | US-052 | Household / multi-user shopping | Consumer | Could Have | Draft | V3 | after V2 | user_space | Architecture §9 | Planned - not in skeleton | - | - | - | Shared list vs private preferences | V3
V3 | US-053 | Add a new domain evaluation model (restaurants, hotels, services) | Admin | Could Have | Clarification Required | V3 | after V2 | evaluation + admin | Architecture §6 (entity_id); EVALUATION_MODEL_SPECS | POST /api/v1/admin/evaluation-models | products, evaluation_models | - | - | Restaurant v1 model evaluates end to end without core changes | Uses the reserved entity_id

## Coverage
Coverage summary (formulas over the Traceability sheet)
Stories by phase and priority
Phase | Must | Should | Could | Total
Phase 1 | 9 | 0 | 0 | 9
Phase 2 | 5 | 1 | 0 | 6
Phase 3 | 6 | 4 | 0 | 10
Phase 4 | 4 | 9 | 0 | 13
Phase 5 | 2 | 1 | 0 | 3
V2 | 0 | 4 | 4 | 8
V3 | 0 | 0 | 4 | 4
Total | 26 | 19 | 8 | 53
Stories by status
Status | Count
Draft | 40
Clarification Required | 13
Ready for Development | 0
In Development | 0
Ready for QA | 0
Done | 0
Blocked | 0
Total | 53
Mapping completeness checks
Check | Value
Stories mapped | 53
Stories with endpoints in the API skeleton | 44
Stories whose endpoint is planned (not yet specified) | 7
Stories reusing V1 endpoints | 1
Negative requirements (no endpoint) | 1
Check: categories add up to stories mapped | OK
Source: story data from Review_Master_User_Stories.xlsx; mapping built from the architecture package. Phase and sprint columns come from DELIVERY_PLAN.md.

## Endpoint index
API endpoint -> stories (generated from the mapping at build time)
Method | Path | Stories | Note
GET | /api/v1/admin/audit-log | US-037
POST | /api/v1/admin/evaluation-model-versions/{version_id}/publish | US-034
GET | /api/v1/admin/evaluation-models | US-034
POST | /api/v1/admin/evaluation-models | US-053
GET | /api/v1/admin/evaluation-models/{model_id} | US-034
POST | /api/v1/admin/evaluation-models/{model_id}/versions | US-034
POST | /api/v1/admin/feedback/{feedback_id}/moderate | US-017
GET | /api/v1/admin/integrations | US-038
GET | /api/v1/admin/mappings/queue | US-035
POST | /api/v1/admin/mappings/{item_id}/resolve | US-035
GET | /api/v1/admin/moderation/queue | US-017
GET | /api/v1/admin/users | US-033
PUT | /api/v1/admin/users/{user_id}/roles | US-033
GET | /api/v1/api-keys | US-040, US-048
POST | /api/v1/api-keys | US-040
DELETE | /api/v1/api-keys/{key_id} | US-040
POST | /api/v1/auth/login | - | Sign-up/login/session: no explicit user story (see gap G1)
POST | /api/v1/auth/logout | - | Sign-up/login/session: no explicit user story (see gap G1)
POST | /api/v1/auth/refresh | - | Sign-up/login/session: no explicit user story (see gap G1)
POST | /api/v1/auth/signup | - | Sign-up/login/session: no explicit user story (see gap G1)
POST | /api/v1/auth/verify-email | - | Sign-up/login/session: no explicit user story (see gap G1)
POST | /api/v1/chat/messages | US-042
POST | /api/v1/comparisons | US-018, US-019
POST | /api/v1/evaluations/{evaluation_id}/explanation | US-012
POST | /api/v1/evidence | US-036, US-049
GET | /api/v1/evidence/{evidence_id} | US-011
GET | /api/v1/evidence/{evidence_id}/versions | US-011
POST | /api/v1/evidence/{evidence_id}/versions | US-036
POST | /api/v1/expert-assessments/{assessment_id}/review | US-032
POST | /api/v1/expert-cases | US-029
POST | /api/v1/expert-cases/{case_id}/assessments | US-031
POST | /api/v1/expert-cases/{case_id}/assign | US-030
GET | /api/v1/notification-settings | US-028
PUT | /api/v1/notification-settings | US-028
GET | /api/v1/preferences | US-024
PUT | /api/v1/preferences | US-024
GET | /api/v1/price-alerts | US-027
POST | /api/v1/price-alerts | US-027
DELETE | /api/v1/price-alerts/{alert_id} | US-027
GET | /api/v1/products | US-005
POST | /api/v1/products/corrections | US-003
POST | /api/v1/products/identify | US-001, US-002
GET | /api/v1/products/{product_id} | US-004
POST | /api/v1/recommendations | US-022, US-023
POST | /api/v1/recommendations/requirements | US-021
GET | /api/v1/saved-products | US-007
POST | /api/v1/saved-products | US-007
DELETE | /api/v1/saved-products/{saved_id} | US-007
GET | /api/v1/users/me | US-033
GET | /api/v1/variants/{variant_id} | US-004, US-006
GET | /api/v1/variants/{variant_id}/alternatives | US-020
GET | /api/v1/variants/{variant_id}/community | US-015, US-016
GET | /api/v1/variants/{variant_id}/evaluation | US-008, US-009, US-010
GET | /api/v1/variants/{variant_id}/evaluation/history | US-013
POST | /api/v1/variants/{variant_id}/feedback | US-014
GET | /api/v1/variants/{variant_id}/offers | US-025
GET | /api/v1/variants/{variant_id}/price-history | US-026
GET | /api/v1/webhooks | US-041
POST | /api/v1/webhooks | US-041
DELETE | /api/v1/webhooks/{webhook_id} | US-041
GET | /api/v1/webhooks/{webhook_id}/deliveries | US-041
POST | /api/v1/webhooks/{webhook_id}/deliveries/{delivery_id}/replay | US-041
GET | /healthz | - | Platform operation (probes), no user story
GET | /readyz | - | Platform operation (probes), no user story